## Sheet1
Task Name | Duration | Resource Names | Cost | Material Cost
Foundation | 90 days |  | $11,520.00
Drilling well | 10 days | Cribber | $1,280.00 | $250,000.00
Installing Soldier Piles | 10 days | Labour | $1,280.00 | $100,000.00
Excavation | 10 days | Cribber | $1,280.00 | $150,000.00
Concrete Footing | 10 days | Cribber | $1,280.00 | $50,000.00
Steel erection | 10 days | Cribber | $1,280.00 | $50,000.00
Concrete base | 10 days | Mason | $1,280.00 | $100,000.00
Concrete walls | 10 days | Mason | $1,280.00 | $150,000.00 |  | 12429548
Concrete columns | 10 days | Mason | $1,280.00 | $250,000.00
Concrete Slab | 10 days | Mason | $1,280.00 | $150,000.00 | 1250000
Exterior | 200 days |  | $23,590.00
Walls bricking | 15 days | Mason | $1,920.00 | $50,000.00
Roof building | 15 days | Roofer | $1,920.00 | $50,000.00
Installation of Ceiling | 20 days | Roofer | $2,560.00 | $50,000.00
Shingle Roofing | 20 days | Roofer | $2,560.00 | $20,000.00
Aluminium trimming | 15 days | Ironworker | $1,920.00 | $10,000.00
Installing Soffits | 15 days | Ironworker | $1,920.00 | $20,000.00
Installing Fascia | 10 days | Roofer | $1,280.00 | $10,000.00
Installing Eavestrough | 15 days | Roofer | $1,920.00 | $10,000.00
Doors and Windows | 15 days | Carpenter | $1,920.00 | $20,000.00
Driveway asphalt surfacing | 20 days | Asphalt Contractor | $550.00 | $30,000.00
Installation of patio | 10 days | Landscaper | $1,280.00 | $30,000.00
Installation of shrubs | 10 days | Landscaper | $1,280.00 | $20,000.00
Installation of front and back sodding | 20 days | Landscaper | $2,560.00 | $50,000.00 | 360000
Interior | 70 days |  | $10,320.00
Ceiling | 10 days | Mason | $1,280.00 | $50,000.00
Flooring | 10 days | Mason | $1,280.00 | $50,000.00
Stairs | 10 days | Labour | $1,280.00 | $10,000.00
Bedroom construction | 10 days | Mason | $1,280.00 | $10,000.00
Bathroom construction | 10 days | Mason | $1,280.00 | $10,000.00
Installing floor carpet | 5 days | Tiler | $640.00 | $5,000.00
Pest control treatment | 5 days | Pest-Control Technician | $2,000.00
Painting walls | 5 days | Painter | $640.00 | $5,000.00
Furniture Installation | 5 days | Carpenter | $640.00 | $50,000.00 | 190000
Utilities | 50 days |  | $8,880.00
HVAC | 7 days | HVAC Technician | $300.00 | $150,000.00
Electricity | 7 days | ElectricianA | $500.00 | $100,000.00 |  | 1
communication wiring | 5 days | ElectricianB | $500.00 | $50,000.00 |  | 2
Room and appliance outlet fitting | 7 days | ElectricianC | $500.00 | $5,000.00 |  | 3
Plumbing of Kitchen | 5 days | Plumber for Kitchen | $640.00 | $10,000.00
Plumbing of Bathrooms | 5 days | Plumber for Bathroom | $640.00 | $30,000.00
Installing Laundry machines | 2 days | TechnicianA | $400.00 | $50,000.00
Lighting installation in Rooms | 5 days | ElectricianD | $500.00 | $10,000.00
Installation of External lightings | 7 days | ElectricianA | $500.00 | $10,000.00 |  |  | 1250000
Installing External Backup power supply generator | 5 days | TechnicianA | $1,000.00 | $150,000.00 |  |  | 360000
Installation if Furnaces | 7 days | TechnicianA | $1,400.00 | $150,000.00 |  |  | 190000
Elevator | 10 days | TechnicianA | $2,000.00 | $350,000.00 | 1065000 |  | 1065000
Security | 30 days |  | $6,224.00 |  |  |  | 220000
Installation of Cameras | 4 days | TechnicianA | $800.00 | $10,000.00 |  |  | 3085000
Installation of Erect Fence | 4 days | Carpenter | $512.00 | $10,000.00
Installation of Security Room | 4 days | TechnicianA | $800.00 | $150,000.00
Installation of security camera screens | 4 days | TechnicianB | $800.00 | $20,000.00
Installation of secure Lockers | 4 days | Carpenter | $512.00 | $5,000.00
Installation of Secrity entrance system | 4 days | TechnicianA | $800.00 | $10,000.00
Installation of security key-card lock doors | 5 days | TechnicianA | $1,000.00 | $5,000.00
Fire alarm System | 5 days | TechnicianA | $1,000.00 | $10,000.00 | 220000